# School-Located Vaccine Event (SLVE) Action Plan

This checklist mirrors the [**SLVE training module**](https://eziz.org/assets/docs/shotsforschool/Training/SLVE/story.html) **(**[**bit.ly/SLVETraining**](https://bit.ly/SLVETraining)**)** and can be completed by SLVE organizers

##  Pre-Planning Phase (4-6 Months Prior to the SLVE)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Obtain school buy-in a & leadership support*** Meet with district leadership, school principal or other individuals with influence in the school community
 | [**CDPH SLVE Letter of Support**](https://www.cdph.ca.gov/Programs/CID/DCDC/CDPH%20Document%20Library/Immunization/OfficeLetterSupport-SLVE.pdf) **(bit.ly/CDPHSLVELetterofSupport)** | *(Example: Coordinator, Volunteer, Vaccination Partner)* |  |  | [ ]  |
| **Determine if MOU/FUA are needed*** Consult with district leadership or school principal to understand what, if any, agreements are required.
 | **[MOU/FUA Samples on Shots For School – SLVE Resource (](https://www.cdph.ca.gov/Programs/CID/DCDC/Pages/Immunization/School/resources-clinics.aspx)**[**[bit.ly/CDPHSLVEResources)](https://www.cdph.ca.gov/Programs/CID/DCDC/Pages/Immunization/School/resources-clinics.aspx)**](https://bit.ly/CDPHSLVEResources) |  |  |  | [ ]  |
| **Determine intended audience for SLVE**  | * Students
* Staff
* Community members
* Nearby schools
* Family members
 |  |  |  | [ ]  |

# Pre-Planning Phase (4-6 Months Prior to the SLVE)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Identify which vaccines to include in your SLVE*** Based on participant needs, ages, and time of year, determine what type(s) of vaccines you will offer
 | * Hep B
* Flu
* Polio
* DTaP
* HPV
* MMR
* Tdap
* Varicella
* COVID-19
* Meningococcal B
* Meningococcal ACWY
 |  |  |  | [ ]  |
| **Select vaccination partner*** Begin with entities with whom you already have a relationship
* Examples: Local health department, community health clinics, pharmacies, school-based health centers
 | * Can partner offer all immunizations and resources in needed languages (i.e., screening forms and bilingual staff)?
* Can partner vaccinate all ages in your population?
* Can partner fulfill the requirements of your FUA/MOU?
* Will there be any cost? [**SLVE Cost Guide**](https://www.cdph.ca.gov/Programs/CID/DCDC/Pages/Immunization/School/resources-clinics.aspx) **(bit.ly/CDPHSLVEResources)**
* Will insurance status of participants be a factor?
 |  |  |  | [ ]  |

# Pre-Planning Phase (4-6 Months Prior to the SLVE)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Meet with all partners to ensure Pre-Planning Phase is complete and prepare for Planning Phase 1** |  |  |  |  | [ ]  |

## This Area Left Intentionally Blank

## Planning Phase 1 (3-4 Months Prior to the SLVE)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Select date and time**Consider combining with other school events and/or offering grade and seasonal specific events:* + - Tdap Events (6th grade)
* Fall Flu Events
* Adolescent Immunization Week (1st week of April)
* Preteen Vaccine Week (1st week of March)
* HPV Vaccine Week (2nd week of August)
* National Immunization Awareness Week (last week of April)
 | * During school or after hours
* On a normal school day or summer or holiday break
* Combine with another school event/activity
* With/without parents/guardians
 |  |  |  | [ ]  |
| **Ensure completion of required MOU/FUA agreements, if applicable** |  |  |  |  | [ ]  |

## Planning Phase 1 (3-4 Months Prior to the SLVE)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Begin promoting SLVE:*** Determine which platforms you will use to promote your event
* Determine which trusted messengers in your community can be leveraged to amplify your message and engage your families
 | [**SLVE Promotional Toolkit**](https://www.cdph.ca.gov/Programs/CID/DCDC/Pages/Immunization/School/resources-clinics.aspx)[**(bit.ly/CDPHSLVEResources)**](https://bit.ly/CDPHSLVEResources) * Robocalls
* Text-blasts
* Email
* School newsletter
* Website
* Marquee screen/sport event screen
* District/school calendar
* Social media
* Other:
 |  |  |  | [ ]  |
| **Determine what promotional materials your SLVE will need** | * Banners
* Flyers
* Posters
 |  |  |  | [ ]  |
| **Ask community-based organizations (CBOs) to help promote*** Distribute information to their networks
 | * Libraries
* Youth programs
* Faith based organizations
* Recreation centers
* After school programs
* Food banks
* Local businesses
* Chamber of commerce
* Other schools
 |  |  |  | [ ]  |

## Planning Phase 1 (3-4 Months Prior to the SLVE)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Distribute paper or electronic consent forms provided by vaccination partner*** Consent form collection rates are better when teachers are actively involved with reminders and collection
 | For partners using My Turn, QR codes or URL can be created for advance digital registration and consent[**My Turn**](https://mycavax.cdph.ca.gov/s/my-turn) **(**[**bit.ly/MyTurnRegistration)**](https://bit.ly/MyTurnRegistration)  |  |  |  | [ ]  |
| **Begin recruiting volunteers to help at the event** | **List names and contacts of volunteers**1. 2. 3. |   |  |  | [ ]  |
| **Select a space/location*** Classroom, multi-purpose room, cafeteria, library, or similar space

Confirm availability of tables and chairs for use at event | **Considerations for location:*** Large, open space, minimal obstacles
* Waiting area for students to line up
* Separate entry and exit doors
* Easy access to restrooms
* Power source
* Wi-Fi access

[**SLVE Sample Vaccination Area Setups**](https://www.cdph.ca.gov/Programs/CID/DCDC/Pages/Immunization/School/resources-clinics.aspx)[**(bit.ly/CDPHSLVEResources)**](https://bit.ly/CDPHSLVEResources) |  |  |  | [ ]  |

## Planning Phase 1 (3-4 Months Prior to the SLVE)

## Optional Coordinator Responsibilities

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Identify optional incentives that can be donated by the community or purchased** | [**SLVE Incentive Resources**](https://www.cdph.ca.gov/Programs/CID/DCDC/Pages/Immunization/School/resources-clinics.aspx)[**(bit.ly/CDPHSLVEResources)**](https://bit.ly/CDPHSLVEResources) |  |  |  | [ ]  |
| **Meet with all partners to ensure Planning Phase 1 is complete and prepare for Planning Phase 2** |  |   |  |  | [ ]  |

## This Area Left Intentionally Blank

## Planning Phase 2 (1-2 Weeks Prior to the SLVE)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Send frequent reminders to encourage and increase participation*** Refer to promotional toolkit for communication templates
 | [**SLVE Promotional Toolkit**](https://www.cdph.ca.gov/Programs/CID/DCDC/Pages/Immunization/School/resources-clinics.aspx)[**(bit.ly/CDPHSLVEResources)**](https://bit.ly/CDPHSLVEResources)  |  |  |  | [ ]  |
| **Finalize plans with volunteers** | * Consider creating a volunteer shift schedule
 |  |  |  | [ ]  |
| **Finish collecting all paper consent forms 1-2 days prior to SLVE, if applicable****Run a report a day in advance if using electronic registration to determine expected participation** |  |  |  |  | [ ]  |
| **Meet with all partners to ensure Planning Phase 2 is complete and prepare for Day of SLVE**  |  |  |  |  | [ ]  |

## Day of SLVE

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Meet with vaccination partner and volunteers to ensure set-up, staff/volunteers, supplies are in place for the SLVE** | [**SLVE Student Identification Protocol**](https://www.cdph.ca.gov/Programs/CID/DCDC/Pages/Immunization/School/resources-clinics.aspx)[**(bit.ly/CDPHSLVEResources)**](https://bit.ly/CDPHSLVEResources)  |  |  |  | [ ]  |
| **Coordinate volunteers** |  |  |  |  | [ ]  |
| **Provide vaccination partner with classroom map and bell/recess schedule** (if conducting event during school hours) |  |  |  |  | [ ]  |
| **Place promotional and directional signage to guide people to the SLVE** |  |  |  |  | [ ]  |
| **Have at least one school representative present to lock up the facility** |  |  |  |  | [ ]  |

## Day of SLVEOptional Coordinator Responsibilities

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Take pictures during event and capture narrative to share outcomes with school and community**This will help with marketing efforts for future SLVEs |  |  |  |  | [ ]  |

## This Area Left Intentionally Blank

## Post-SLVE

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Steps** | **Considerations, Resources, and Links** | **Responsible Party** | **Timeline** | **Comments** | **Status** |
| **Participate in a debrief meeting with the planning/vaccination partner if requested** |  |  |  |  | [ ]  |
| **Complete an evaluation survey if the vaccination partner requests** | [**SLVE Evaluation Survey**](https://www.cdph.ca.gov/Programs/CID/DCDC/Pages/Immunization/School/resources-clinics.aspx)[**(bit.ly/CDPHSLVEResources)**](https://bit.ly/CDPHSLVEResources) |  |  |  | [ ]  |
| **Schedule return event dates:** Ensure that participants know when their next vaccinations are due, if appropriate, and when additional SLVEs will be held |  |  |  |  | [ ]  |

## SLVE Notes

**Notes:**

**This Area Left Intentionally Blank for SLVE Notes**

## School-Located Vaccine Event Information

|  |
| --- |
| **If vaccinating partner is using My Turn, insert QR codes or URL in advance of your event for digital registration and consent.****QR Code:** **URL:** |

## Coordinator Contact Information

|  |  |  |
| --- | --- | --- |
| **School Name:** | **Event Date #:** | **Event Date #2 (If applicable):** |
| **Coordinator Name:** | **Coordinator Phone:** | **Coordinator Email:** |
| **Secondary Contact:** | **Contact Phone:** | **Contact Email:** |

## Vaccinating Partner Information

|  |  |  |
| --- | --- | --- |
| **Vaccinating Partner Contact:** | **Partner Phone:** | **Partner Email:** |
| **Secondary Contact:** | **Contact Phone:** | **Contact Email:** |

**Questions:** Email **Schoolvaxteam@cdph.ca.gov**for questions and support.